## Slide 1: Liquidity Risk Management Plan
LRMP PROJECT · KICK-OFF
Kick-off with Covéa Insurance plc
DATE
3 November 2026
FORMAT
Kick-off meeting · 45 minutes
PRESENTED BY
Covéa Group, LRMP project team
Notes: Agenda and timing (45 min): introduction 2 min; what the LRMP is 8 min; Group calendar 5 min; what we need from you 6 min; assumptions already secured 4 min; reporting mock-up walkthrough 10 min; next steps 3 min; your questions 7 min. Purpose of the session: explain the LRMP, share the calendar, agree what we need from Covéa Insurance, and walk through the reporting template.

## Slide 2: A forward-looking plan to manage liquidity risk
THE LRMP
Solvency II review (Directive (EU) 2025/2), applicable from 30 January 2027.
What it is
Projects cash inflows, outflows and liquid assets, under normal and stressed conditions.
Two time horizons
Short term: up to 3 months. Medium/long term: beyond 3 months.
Group level
One Group plan for the ACPR, built from each entity's inputs and updated at least annually.
THE SIX SECTIONS OF AN LRMP
1
Overall assessment
2
Assumptions
3
Cash flow projections
4
Buffers of liquid assets
5
Liquidity risk indicators
6
Other information
Notes: What is the LRMP (8 min, including what it means for Covéa Insurance). Key message: it is a plan, not a single ratio. It projects cash inflows and outflows, the buffer of liquid assets and liquidity risk indicators, under normal and stressed conditions. Two horizons: short term (up to 3 months) and medium/long term (beyond 3 months). It is drawn up by insurers and also at group level (Art. 246a): the Group submits one plan to the ACPR, built from each entity's inputs, and updates it at least annually and after any significant change. Two UK-specific points: even if the PRA does not require a stand-alone LRMP, the Group needs your data; we will agree currency and conversion conventions (GBP/EUR). The six sections come from the draft technical standards (RTS, Art. 3). Status: the RTS were submitted to the Commission in November 2025 and formal adoption was still pending when this deck was written - re-check before the meeting.

## Slide 3: Target agenda
GROUP CALENDAR
Deployment of the LRMP, aligned with the Group Board Committee calendar.
PERIOD
PHASE
KEY ACTIVITIES
DELIVERABLE
2026 Q3
Kick-off
Legal perimeter finalised · Reporting doctrine · Governance and committees · Templates validated and sent to subsidiaries
Scoping note; target template
2026 Q4
Methodology
Production tools developed · Workshops with subsidiaries · Key assumptions justified (stress per subsidiary, sub-group consolidation)
Approved methodology package
2027 Q1
Effective 30/01
Intragroup
Intragroup cash flows (incl. internal reinsurance) · Transferability and liquidity support · Solo LRMP requirements for foreign subsidiaries
Intragroup CF modelling; LRMP dry-run package
2027 Q2
Dry run
Results consolidated · Group / subsidiary iterations where necessary · Short-term and medium/long-term horizons
Complete LRMP draft for ST + MLT stress
2027 Q3
Post-mortem
Results consolidated · Group / subsidiary iterations where necessary · Short-term and medium/long-term horizons
Roadmap for 1st submission; new run calendar
2027 Q4
Validation and submission
ROC in December · Audit and Risk Committee ~5 May · Board ~12 May · Submission within 2 weeks via ONEGATE · Quarterly production
Short-term LRMP submitted to the ACPR
2028
Annual rollover
Preparation and production of the MLT LRMP · Transition to the annual reporting cycle
LRMP ST + MLT
KEY MESSAGES
1st submission to the ACPR scheduled for December 2027, exceptionally, for the Short-Term LRMP
The quarterly update process of the Short-Term LRMP is expected to generate a material recurring workload
To ensure readiness before the first regulatory submission, the Group plans a dry run exercise at mid-2027
Notes: Target agenda (5 min). Walk down the seven phases. 2026 Q3 kick-off: legal perimeter finalised, subsidiary reporting doctrine, governance and committee framework, subsidiary reporting templates validated and communicated (deliverables: scoping note, target template). 2026 Q4 methodology: development of production tools, workshops with subsidiaries, justification of impacting assumptions - consolidation at sub-group level for PRE, stress for each subsidiary (deliverable: approved methodology package). 2027 Q1 intragroup: modelling of intragroup cash flows including internal reinsurance, assessment of transferability and intragroup liquidity support, listing of solo LRMP requirements for foreign subsidiaries; the LRMP requirement takes effect on 30/01/2027 (deliverables: intragroup CF modelling, LRMP dry-run package). 2027 Q2 dry run: consolidation of results, Group/subsidiary iterations where necessary, short-term and medium/long-term horizons (deliverable: complete LRMP draft for ST + MLT stress). 2027 Q3 post-mortem: same activities (deliverables: LRMP roadmap for first submission, new run calendar). 2027 Q4 validation and submission: ROC in December; Audit and Risk Committee about 5 May; Board about 12 May; submission within 2 weeks; ONEGATE submission; quarterly production (deliverable: short-term LRMP submitted to the ACPR). 2028 annual rollover: preparation and production of the MLT LRMP, transition to the annual reporting cycle (deliverable: LRMP ST + MLT). Key messages are in the bottom strip.

## Slide 4: Three inputs, by 1 December 2026
WHAT WE NEED FROM YOU
Short notes or tables are enough.
1
Is a solo LRMP required?
Check with your regulator and tell us the answer, with the reference of the text.
1 Dec 2026
2
Transferability and fungibility of own funds
A short note on legal, regulatory, tax and currency constraints, and on the time needed to transfer.
1 Dec 2026
3
Liquidity reporting and aligned shocks
List the liquidity reporting you are subject to, and propose shocks aligned with it, or at least with your ORSA and the Group's PPR scenarios.
1 Dec 2026
Whatever your regulator answers, the Group needs your data for its own plan. We will agree the currency convention (GBP / EUR) together.
Notes: What we need from you (6 min). Three inputs, all due on 1 December 2026. (1) Check with your regulator whether a stand-alone LRMP is required, and give us the answer and the reference. (2) A short note on the transferability and fungibility of own funds: legal, regulatory, tax and currency constraints, ring-fenced or restricted funds, dividend approvals, time needed to transfer. (3) An inventory of the liquidity reporting you already produce (report, recipient, frequency, horizon, content), with stress shocks aligned to it - or at least to your ORSA and the Group's preventive recovery plan (PPR) scenarios. Remind them that, whatever the regulator's answer, the Group needs their data for its own plan, and that currency conventions (GBP/EUR) will be agreed together.

## Slide 5: What is already secured
ASSUMPTIONS
Working assumptions fixed by the Group: you do not need to define them.
SHORT-TERM HORIZON
3 months
Cash flows projected up to three months ahead.
MEDIUM / LONG-TERM HORIZON
1 year
Cash flows projected up to one year ahead.
LIQUIDITY INDICATOR
(Inflows + Buffer) / Outflows
Already calculated by the Group.
Scenarios start from the Group's PPR scenarios.
Updates short-term plan quarterly, medium/long-term plan annually.
Notes: Assumptions already secured (4 min). Short-term horizon is 3 months; medium/long-term horizon is 1 year. A liquidity indicator is already built and calculated on the Group side: (inflows + liquidity buffer) / outflows. Stress scenarios start from the Group's preventive recovery plan (PPR) scenarios, and your proposals will be compared with them. Update rhythm: short term quarterly, medium/long term annual.

## Slide 6: Reporting template
REPORTING TEMPLATE
One reporting framework, less duplication.
FOR VALIDATION
1. Template
TO IDENTIFY
1. Methodology gaps
2. Anticipated challenges
Methodology & User Guide
Sheets « ReadMe » & « Assumptions »
Practical translation of the EIOPA RTS requirements
Full traceability to the regulatory provisions
Reporting guidance for contributors
Targeted simplifications where appropriate
Built-in consistency checks to identify reporting gaps
Glossary for a common understanding across entities
Projections & Liquidity Buffer
Sheets « Cashflows_ST_* », « Buffer_ST » and « LRIs »
Cash flow projections under baseline and stressed scenarios
Regulatory projection horizon and reporting granularity
Documented assumptions and stress calibrations
Harmonized classification framework for liquid assets
Methodology frozen for the Dry Run; enhancements possible after entity feedback
Automated Short-Term Liquidity Indicators (when stabilized)
Qualitative information
Sheets « Assumptions » & « Other_Info »
Liquidity constraints and limitations
Intragroup liquidity support arrangements
Qualitative analysis to inform the supervisory assessment
Other attention points
Contained in the template
Internal reinsurance cash flows broken down by counterparty entity
Legal, regulatory or operational constraints on liquidity transferability across jurisdictions
→ Walkthrough the template
INSERT THE MOCK-UP HERE: Insert > Object > Create from file (Excel). Then delete this note.
Notes: Reporting template and walkthrough (10 min). Four blocks: (1) Methodology and user guide - sheets ReadMe and Assumptions: practical translation of the EIOPA RTS, traceability to the provisions, guidance for contributors, targeted simplifications, built-in consistency checks, glossary. (2) Projections and liquidity buffer - sheets Cashflows_ST_*, Buffer_ST and LRIs: baseline and stressed projections, regulatory horizon and granularity, documented assumptions and stress calibrations, harmonised classification of liquid assets, methodology frozen for the dry run (enhancements possible after entity feedback), automated short-term liquidity indicators once stabilised. (3) Qualitative information - sheets Assumptions and Other_Info: liquidity constraints, intragroup liquidity support arrangements, qualitative analysis for the supervisory assessment. (4) Other attention points: internal reinsurance cash flows by counterparty entity; legal, regulatory or operational constraints on transferability of liquidity across jurisdictions. Ask for validation of the template and for methodology gaps and anticipated challenges. Then open the embedded mock-up and walk through it.

## Slide 7: Next steps and your questions
NEXT STEPS
A named correspondent, regular touchpoints and a support kit.
WAYS OF WORKING
A named LRMP correspondent in your entity
Touchpoints every two months, weekly during the dry run
Support kit shared in Q1 2027
Action | Owner | By
Nominate your LRMP correspondent | Covéa Insurance | 10 Nov 2026
Share this deck and the mock-up | Group | This week
Deliver the three inputs | Covéa Insurance | 1 Dec 2026
Next touchpoint | Both | Jan 2027
Your questions
[Name, role and e-mail of the Group LRMP project manager]
Notes: Next steps (3 min) then questions (7 min). Ways of working: a named correspondent in Covéa Insurance, touchpoints every two months and weekly during the dry run, a support kit shared in Q1 2027, questions at any time to the Group LRMP project team, and escalation to the Group steering committee if needed. Go through the action table and confirm owners and dates - only 1 December is fixed, the other dates are proposals. During questions: capture each question and its owner, and send written answers within the week. Add the project manager's contact details in the bottom band before the meeting.